## Slide 1: Mass Management & Margins
And 696-JPL Parallels

## Slide 2: The Problem
WE WANT TO TRACK MASS
  Throughout the design process
  Prevents surprises close to launch/bag day
  Allows you to redistribute allocations
We also want to maintain margins
  That is, don’t design for exactly 120 lbm

## Slide 3: The Problem
However, we want to avoid margin stacking
A system (SV, robot) is made up of subsystems
  JPL:
    Structure
    Command & data handling (C&DH)
    Propulsion
    Guidance, navigation, and control (GNC)
  696:
    Drivebase
    Elevator
    Intake
    Climber
Each subsystem has some components, which may be made up of other components, etc…

## Slide 4: The Problem
Example:
  LV can lift 1000 lbm
  SV mass target is 900 lbm (10% margin)
  3 subsystem engineers are given 300 lbm allocations
  Each SS engineer sets a mass target of 270 lbm (10% margin)
  Each SS is made up of boxes
  Each box PDM adds 10% margin…
SV mass ends up being 600 lbm
Wastes 40% of LV capacity
Results in diminished capabilities

## Slide 5: The Problem
There’s a military joke with a similar theme:
“The captain wants everyone to meet at 0600, so the master sergeant wants folks to arrive at 0545, and when it finally hits the corporal people are told to show up at midnight.”

## Slide 6: The Solution
Set up clear definitions of where margins are held
  Everyone doesn’t just add 10% margin to their deliverable
There’s a standard for this!
  ANSI/AIAA S-120A-2015
  “Mass Properties Control for Space Systems”

## Slide 7: The Solution
Basic Mass
Mass Growth Allowance
Mass Margin
Mass Reserve
Predicted Mass
Allowable Mass
Mission Limit
0

## Slide 8: Mission Limit
Dictated by LV capacity (or FRC rules, i.e., 120 lbm)
Generally nonnegotiable
Basic Mass
Mass Growth Allowance
Mass Margin
Mass Reserve
Predicted Mass
Allowable Mass
Mission Limit
0

## Slide 9: Mass Reserve
Set at the system or project level
Often fairly small, e.g. 5%
Designed to account for:
  Measurement uncertainty
  Non-SV stuff
    E.g. SV-to-LV umbilicals
  Operational contingency
    LVs have slightly less lift capacity in strong winds
  In our case, might also include repairs etc. at comp
Mass reserve should not be invaded by design
Basic Mass
Mass Growth Allowance
Mass Margin
Mass Reserve
Predicted Mass
Allowable Mass
Mission Limit
0

## Slide 10: Allowable Mass
The mission limit minus the mass reserve
The mass that “you have to work with”
This is allocated out to subsystems
  Chunks of it are then allocated out to e.g. boxes
No need to allocate less than 100% of allowable mass
  That’s what mass margin is for
Basic Mass
Mass Growth Allowance
Mass Margin
Mass Reserve
Predicted Mass
Allowable Mass
Mission Limit
0

## Slide 11: Basic Mass
In archaic JPL parlance, “current best estimate”
What you think the mass of your (subsystem/ box/ component) is
I.e., “if I open it in Solidworks and hit the ‘Mass Properties’ button, what does it say?”
Basic Mass
Mass Growth Allowance
Mass Margin
Mass Reserve
Predicted Mass
Allowable Mass
Mission Limit
0

## Slide 12: Mass Growth Allowance
“How much heavier do I think the actual item will be than my basic mass?”
Is a combination of many factors:
  Maturity of design
    NASA has a standard for this
  Uncertainty of what components are needed
  Predicted mass of untracked items
    E.g., we might estimate that cabling will add 5 lbm to the drivebase mass
    Or, “fasteners will probably add 5% to the mass of the elevator”
Could be zero, e.g. with COTS parts
Basic Mass
Mass Growth Allowance
Mass Margin
Mass Reserve
Predicted Mass
Allowable Mass
Mission Limit
0

## Slide 13: Predicted Mass
Basic mass + MGA
If your estimates are good, you should be able to weigh the finished item and have it be very close to the predicted mass
Basic Mass
Mass Growth Allowance
Mass Margin
Mass Reserve
Predicted Mass
Allowable Mass
Mission Limit
0

## Slide 14: Mass Margin
The difference between “how much mass you have to work with” and “how much mass you think you’ll need”
In general, negative mass margin (i.e. PM > AM) is a bad thing
However, if another subsystem is underweight, some of their AM can be reallocated to you
  This needs to happen at the system or project level
  Never count on someone else having mass margin to spare, though
Basic Mass
Mass Growth Allowance
Mass Margin
Mass Reserve
Predicted Mass
Allowable Mass
Mission Limit
0

## Slide 15: Margin Governance
Basic Mass
Mass Growth Allowance
Mass Margin
Mass Reserve
Predicted Mass
Allowable Mass
Mission Limit
0
These are held at the system/project level
These are held at the subsystem level or lower (recursively)

## Slide 16: Extensibility
These same concepts & terms can be used for any quantifiable resource!
  Time
    Mission limit is 46 days, 1 hour, 30 minutes
  Money
    Mission limit might fluctuate based on fundraising
  Power
    More difficult, given steady-state vs. spike loads

## Slide 17: Backup Slides

## Slide 18: MGA Based on Maturity